| SOUTHEAST HORSERADISH GROWERS ASSOCIATION STATEMENT OF WORK |
| --- |
| Task #1 – Finalize the Risk Management Education Plan |
| Sub-task | Responsible Entity (If other than applicant) | Completion Date (Number of days after project start date) | RMA Role | Deliverable |
| Sub-task 1.1: Initial planning meeting with project partners. | Project Director, working with partners | Within 30 days, continue as needed throughout project period | RMA will approve selected sub-contractors in advance. | Project partners are aware of responsibilities in the project. |
| Sub-task 1.2: Identify audience and the behavior to target. | Project Director, working with partners | Within 30 days |  | Specific groups are identified. |
| Sub-task 1.3: Plan specific workshops; work with partners to develop program and agenda. | Project Director, working with partners | Within 30 days | Work with Project Director to plan workshops. | Workshops are planned. |
| Sub-task 1.4: Confirm specific locations and logistics for each workshop. | Project Director, working with partners | Within 60 days | Review and approve delivery plan. | Workshop locations and logistics are confirmed. |
| Sub-task 1.5: Work with partners on program content and confirm speakers. | Project Director, working with partners | Within 60 days | Review and approve in advance all producer’ training plans. | Speakers are confirmed. |
| Sub-task 1.6: Work with speakers to develop workshop topics. | Project Director, working with partners | Within 60 days |  | Workshop topics are chosen. |

| SOUTHEAST HORSERADISH GROWERS ASSOCIATION STATEMENT OF WORK |
| --- |
| Task #2 – An Effective Set of Instructional Materials |
| Sub-task | Responsible Entity (If other than applicant) | Completion Date (Number of days after project start date) | RMA Role | Deliverable |
| Sub-task 2.1: Complete a review of existing instructional materials. | Program workgroup | Within 30 days. |  | Existing instructional materials are reviewed and identified for use. |
| Sub-task 2.2: Identify gaps in existing instructional materials. | Program workgroup | Within 45 days. |  | Gaps in existing instructional materials are identified. |
| Sub-task 2.3: Modify existing instructional materials. | Program workgroup | Within 60 days. | Review and approve instructional materials. | Instructional materials are prepared. |
| Sub-task 2.4: Develop new instructional materials. | Program workgroup | Within 60 days. | Review and approve instructional materials. | Instructional materials are prepared. |
| Sub-task 2.5: Prepare notebooks and handouts for workshop sessions. | Program workgroup | Within 90 days | Review and approve notebooks and handouts. | Workshop notebooks and handouts are prepared. |

| SOUTHEAST HORSERADISH GROWERS ASSOCIATION STATEMENT OF WORK |
| --- |
| Task #3 – Increased Risk Management Awareness Through Effective Promotion |
| Sub-task | Responsible Entity (If other than applicant) | Completion Date (Number of days after project start date) | RMA Role | Deliverable |
| Sub-task 3.1: Publicize workshops and program in newsletters of all partners. | Program workgroup. | In the November, December, January, February and March newsletters. | Review newsletter in advance. RMA logo will be prominently displayed in materials. | Producers are aware of educational activities. |
| Sub-task 3.2: Conduct outreach for program. Publicize with press releases and announcements to local and regional papers, including traditional agricultural media. | Program workgroup. | Within 60 days. | Review press release in advance. RMA logo will be prominently displayed in materials. | Workshops are publicized in 3 newspapers, 3 agricultural media spots and 1 radio interview. |
| Sub-task 3.3: Direct mail workshop brochures to producers using partners’ mailing lists. | Program workgroup. | 2 mailings in November and January. | Review brochure in advance. RMA logo will be prominently displayed in materials. | Producers receive workshops brochures. |

| SOUTHEAST HORSERADISH GROWERS ASSOCIATION STATEMENT OF WORK |
| --- |
| Task #4 – Increased Risk Management Skills Through Effective Training |
| Sub-task | Responsible Entity (If other than applicant) | Completion Date (Number of days after project start date) | RMA Role | Deliverable |
| Sub-task 4.1: Conduct risk management education workshop at annual convention. | Program workgroup. | February 15, 2006 |  | Risk management education workshop is conducted at annual convention. |
| Sub-task 4.2: Conduct 2 risk management education workshops for agribusiness professionals. | Program workgroup. | January 15, 2006 February 1, 2006 | Collaborate on the organization and delivery of training to agribusiness leaders and producer trainers. | Two risk management education workshops for agribusiness professionals are conducted. |
| Sub-task 4.3: Conduct 12 risk management education workshops for producers. | Program workgroup. | 3 by December 31, 2005 6 by January 31, 2006 9 by February 28, 2006 12 by March 31, 2006 | Collaborate on the delivery of risk management education to producers by advising on technical issues relating to risk management education; and assisting in informing crop insurance professionals about producer training activities. | Twelve risk management education workshops for producers are conducted. |
| Sub-task 4.1: Post workshop materials on website. | Program workgroup. | Within 180 days. | Concur in advance on materials to be posted. | Workshop materials are posted on website. |

| SOUTHEAST HORSERADISH GROWERS ASSOCIATION STATEMENT OF WORK |
| --- |
| Task #5 – A Well Documented Program |
| Sub-task | Responsible Entity (If other than applicant) | Completion Date (Number of days after project start date) | RMA Role | Deliverable |
| Sub-task 5.1: Develop an evaluation plan and documentation system for project. | Program workgroup. | On-going |  | Project evaluation plan and documentation system is developed. |
| Sub-task 5.2: Prepare progress reports documenting project activities ( What has been accomplished that quarter ( Key insights ( Potential barriers or problems ( Reconfirm future plans |  | Quarterly January 31, 2006 April 30, 2006 July 31, 2006 October 31, 2006 | Read and respond to report as needed. | Quarterly progress reports are submitted. |
| Sub-task 5.3: Maintain an activity log with the number of individuals attending each workshop | Program workgroup | Quarterly January 31, 2006 April 30, 2006 July 31, 2006 October 31, 2006 |  |  |

| Sub-task 5.4: Prepare a Financial Status Report, documenting the financial status of the project. |  | Quarterly January 31, 2006 April 30, 2006 July 31, 2006 October 31, 2006 | Read and respond to report as needed. | Quarterly Financial Status Reports, are submitted. |
| --- | --- | --- | --- | --- |
| Sub-task 5.5: Prepare a “Request for Advance or Reimbursement”, accompanied by documentation. All funds must be expended prior to the project end date outlined in the Agreement. |  | Quarterly January 31, 2006 April 30, 2006 July 31, 2006 October 31, 2006 | Review request and supporting documents, approve for payment, forward to RMA Finance Office for processing. | Quarterly “Request for Advance or Reimbursement”, accompanied by documentation are submitted. |
| Sub-task 5.6: Prepare final written report which will include: ( An executive summary ( A listing of dates, places, instructors, number of participants and instructional topics for all educational activities conducted. ( An evaluation of the overall project (promotional program, instructional materials, training delivery, success stories, recommendations from project partners that might contribute to improved educational programs in the future.) | Project Director, working with partners. | Earlier of 90 days after completion of the project or December 30, 2006 | Review report and issue project closeout letter to project leader. | Final written report including an executive summary, a listing of dates, places, instructors, number of participants and instructional topics for all educational activities conducted under the agreement and an evaluation of the overall project is submitted to RMA. |